LOCAL ECONOMIC DEVELOPMENT PLAN Severodonetsk City Council Economic growth due to - Efficient management - Innovativeness - Partnership This Plan was prepared with technical support from the Mayors for Economic Growth initiative of the European Commission. It was reviewed by the experts of the World Bank and commended as good by the Mayors for Economic Growth initiative. Its content is owned by and remains sole responsibility of Severodonetsk municipality. Ukraine May, 2019

Content

- Foreword	3

Summary	3

List of tables and schemes	3

Abbreviations	3

Plan introduction	3

Local Economic Development Plan development process	3

Local economic analysis	3

6.1.Local economic structure analysis	3

6.3. Transparent, corruption-free administration that encourages business                              development	3

6.4. Access to financing	3

6.5. Land resources and infrastructure	3

6.6. Legal and institutional base	3

6.7. Skilled labor resources, inclusiveness	3

6.8. External positioning and marketing	3

SWOT analysis	3

Vision and goals	3

Action Plan	3

FINANCING SCHEME.	3

MONITORING INDICATORS AND MECHANISMS.	3

- APPENDICES	3

- Foreword

Dear citizens of Sievierodonetsk, Our famous city is traditionally industrial, scientific, innovative and young! Under conditions of proximity to military actions first under ATO, then JFO, the city has undertaken the mission of the administrative center of Luhansk Oblast and new place of residence for thousands of Luhansk citizens and youth education. As such, the local government is responsible for local economic development and creation of new jobs required not only for permanent residents but also for. citizens who chose the city of Severodonetsk as a new place of residence as a result of occupation of a part of Luhansk Oblast. To accelerate the sustainable and inclusive local economic development, the city of Severodonetsk joined the EU Mayors for Economic Growth Initiative in June 2017. Within the framework of this Initiative, we have developed the Local Economic Development Plan in partnership with private sector and civil society. It aims to implement actions to promote the economic growth of the city, develop business and population employment. This is our first attempt of short-term planning of economic growth, focus on joint projects and actions enabling fast implementation and result achievement. This document also aims to apply basic principles of fair state management, encourage participation of all parties concerned in local economic growth, local governments, business and public representatives, and universities and research institutes. We invite all partners and citizens involved to cooperation in the plan implementation and modern economic creation in our city! Sincerely yours, Secretary of the City Council, Acting Mayor Viacheslav Tkachuk

A copy of this plan is available at:

Andrii Ihorovych Verner – focal person,

Severodonetsk City Council

32 Druzhby Narodiv blv, Severodonetsk, Luhansk Oblast, 93400, Ukraine

e-mail: ekonomika@sed-rada.gov.ua, telephone (0645)70-26-01

- 1. Summary

The city of Severodonetsk is located in the western part of Luhansk Oblast, 255 km from Kharkiv (nearest airport) and 750 km from the capital of Ukraine – Kyiv. The permanent population in the city of Severodonetsk as of January 1, 2018 is 115,013 persons, including 51,434 men and 63,579 women.

The occupation of a part of Luhansk Oblast and the city of Luhansk resulted in undertaking by the city functions of the administrative center of Luhansk Oblast. A large number of offices of state-owned and private companies and organizations, higher education institutions, and IDPs moved to the city. As a result, Sievierodonetsk became a youth center and faced an ambitious goal of the youth retention in the city and its labor and intellect involvement into the city economy.

Severodonetsk joined the EU Mayors for Economic Growth Initiative in June 2017 and started preparing a new planning document of specific purpose – Local Economic Development Plan.

The Local Economic Development Plan was developed on the grounds of analytical studies, statistic data and study of entrepreneurs' opinion. The Plan has been developed in partnership with private sector and civil society according to the Mayors for Economic Growth Initiative standards and aims to solve economic issues of the city.

The SWOT analysis showed that the strengths of economic situation in Severodonetsk lie in gaining the status of the regional center of Luhansk Oblast, which resulted in the inflow of private entities and citizens from the uncontrolled territory of the region to the city. The city economy is diversified and export-oriented; export is fulfilled to the following states: Russian Federation, Hungary, Czech Republic, Belarus, Bulgaria, Poland, and France. The largest import share is from the following countries: Russian Federation, France, Poland, Hungary, and Belarus.

The weaknesses that have a considerable impact on local economic growth are as follows: lack of full motor and railway service with other regions of Ukraine; deteriorated financial activities of entities; loss of traditional sales markets by entities in the city; and outflow of skilled specialists to other regions of Ukraine and abroad.

The city opportunities are based on increase in land resources due to annexation of neighbouring rural areas, as well as introduction of a number of infrastructure projects.

The main threat to the city is the ongoing conflict between Ukraine and Russia in the East of Ukraine.

Based on the local economic structure analysis and SWOT analysis, joint vision was agreed in relation to Severodonetsk development as the administrative center of Luhansk Oblast and potential united territorial community created by joining neighbouring rural communities: “Open and safe community of entrepreneurial success in East Ukraine, management and production innovations. Intellectual scientific center of “green” technologies, efficient infrastructure and productive employment”

Below are the main goals:

1. Improving the system of support to local commodity manufacturer and entering new sales markets.

2. Introducing up-to-date energy efficiency and energy independence mechanisms in the city.

3. Improving competitiveness of citizens due to increase of land resources and infrastructure provision of the city by joining neighbouring rural communities.

To achieve the above goals, the Plan provides for implementing 12 actions, in particular, creating the Economic Growth Agency in Severodonetsk as a tool of cooperation between the government and business, creating a modern business center and implementing a number of joint production and infrastructure projects.

The main sources of this Economic Development Plan financing are the local budget, funds of municipal entities and raised endowment funds.

- 2. List of tables and schemes

Table 1. Action Plan

Table 2.  Financing scheme

Table 3. Monitoring indicators

Table 4. Classification of entities by size (in accordance with the Economic Code of Ukraine)

Table 5. Classification of business entities in Severodonetsk by types of economic activities and quantity of recruited employees

Table 6. Breakdown of private entities in Severodonetsk by number and types of activities

Table 7. Capital investments

Table 8. Volume of sold industrial products

Table 9. Direct investments (registered capital)

Table 10. Volumes of exported – imported services

Table 11. Pre-tax financial results of entities

Table 12. Estimate of cooperation at local level

Fig. 1. Scheme of the Local Economic Development Plan development process

Fig. 2 Structure of Sievierodonetsk economy by number of entities

- 3. Abbreviations

JFO – Joined Forces Operation

LG – Local Government

EU – European Union

UTC – United Territorial Community

IDP – Internally Displaced Person

FEA – Foreign Economic Activity

ITP – Individual Thermal Plant

WG – Working Group

Ent – Entrepreneurs

NPE – Natural Persons – Entrepreneurs

SMB – Small and Medium Businesses

PrJSC – Private Joint Stock Company

TOV – Limited Liability Company

KVED – Standard Industrial Classification of Economic Activities

SPC – Scientific and Production Company

SPE – Scientific and Production Enterprise

PE – Private Enterprise

sq. m – square meters

MM – Mass Media

- 4. Plan introduction

On June 20, 2017, the Severodonetsk City Council joined the EU Mayors for Economic Growth Initiative. We take this step as the city commitment to active promotion to local economic growth and gaining of best European experience.

Local economic growth is critical for the local community in Severodonetsk, which currently fulfils functions of industrial, scientific, educational and administrative center of Luhansk Oblast and requires creation of new jobs not only for permanent citizens of Severodonetsk, but also for internally displaced persons who became new citizens of the community as never before.

Severodonetsk is located in the west of Luhansk Oblast, 255 km away from Kharkiv (nearest airport) and 750 km from the capital of Ukraine – Kyiv. The permanent population in Severodonetsk as of January 1, 2018 is 115,013 persons, including 51,434 men and 63,579 women. As of January 1, 2018, the permanent population was 115,013 persons, including 115,214 (13.2 %) persons 0–15 years old, 70,011 (60.9 %) 16–59 years old; 29,788 (25.9 %) 60 years old and older, against January 1, 2016 when 117,856 persons made the permanent population, including 14,663 (12.4 %) persons 0–14 years old, 82,216 (69.8 %) 15–64 years old, and 20,977 (17.8 %) 65 years old and older. As of January 1, 2018, the average age of population is 44.1; it is 40.6 for men and 46.9 for women. The population migration was negative in 2017, with 583 persons as incomers and 1,234 persons as departures. The quantity of registered unemployed persons at the end of June 2018 is 862 persons, 535 of which are women. As of August 1, 2018, the quantity of internally displaced persons is 51,941.

When higher education institutions, for example, Volodymyr Dahl EastUkrainian National University moved to the city from Luhansk and other occupied cities of Luhansk Oblast, Severodonetsk became the youth center and faced an ambitious target of retaining the youth in the city and involving its labor and intellect into the city economy. These are additionally 12 thousand students.

The city understands the participation in the EU Mayors for Economic Growth Initiative as a powerful mechanism that enables starting the dialogue with business community representatives and improving partnership, laying the ground for economic growth in the territory using the advance European experience.

The Local Economic Development Plan is developed by the community for the first time and is a document of specific purpose in the planning system.

The Local Economic Development Plan is based on the provisions of the Severodonetsk Development Strategy until 2020, annual programs of social and economic development and small and medium business development programs.

The Local Economic Development Plan aims to gain main results of the strategic direction “Business Development”, namely: support to existing structures of small and medium business, expansion of their activity, initiation of private-public partnership, etc.

The Local Economic Development Plan has been developed in partnership with private sector and civil society in accordance with methodical recommendations of the EU Mayors for Economic Growth Initiative.

Expenses for the Plan implementation will be covered in part from the municipal budget, state budget, raised donor funds, loan funds, etc.

- 5. Local Economic Development Plan development process

Work on preparation of the Local Economic Development Plan started from creation of a corresponding working group composed of 18 persons, which was approved by the Order of the Mayor No. 197 dated July 20, 2018. The Working Group included representatives of the local government, deputy corps, business and civil society (see Appendices 1, 2). The gender aspect was taken into account during the Working Group creation.

3 meetings of the Working Group were conducted. All areas of work were presented, discussed at the Working Group meetings and appropriate solutions were made. The Plan development schedule became the main tool of planning process management.

The Local Economic Development Plan was developed on the basis of the following main principles:

| Partnership | Conducting various consultations, discussions, agreements aimed at consensus building in the community. All the parties concerned were invited to participate in solution approval and Local Economic Development Plan development, namely representatives of the government, scientific institutions, associations of entrepreneurs, entities and entrepreneurs, and representatives of the civil society. |
| --- | --- |
| Viability | Planning real sources of financing and volumes of financing |
| Integration | Integration is ensured by active participation of all the parties concerned. |
| Innovation | Including new approaches in management and production procedures, and ensuring the most effective use of available resources |
| Institutional memory | It is based on results received during development of previous strategic documents |
| Subsidiarity | Strategic measures starting from the lowest level (based on the community needs) were identified using local economic development resources |

The following actions were performed at six stages of the Local Economic Development Plan development:

| 1) Planning work arrangement. | 4) Action development. |
| --- | --- |
| 2) Local economic structure analysis. | 5) Public discussion and approval of the Plan. |
| 3) Identification of strategic vision, goals. |  |

The data collection methods included the use of statistic information, data that is publicly available in the Internet, interviews, questioning, conduct of focus groups and on the basis of estimated characteristics of the Working Group members.

It should be noted that some issues were rather difficult for discussion and consensus-building because business representatives were not used to cooperate with the government. Time, joint projects and success history are needed to have such steady cooperation practice. Some information and conclusions taken as a basis of this Plan are rather “soft data” and have no statistic grounds as they were not monitored before.  Moreover, the work which results are set out herein is an extremely critical first step to start sustainable economic growth of the Severodonetsk City Council and should be the basis of future transformations.

The document development process was published on the official web-site of the community. All this ensures the Plan development in accordance with the provisions of the EU Mayors for Economic Growth Initiative.

- 6. Local economic analysis

  - Local economic structure analysis

The local economic structure analysis shows that most entities in the city are concentrated in small business; moreover, small business is mainly represented by micro-business, i. e. private entrepreneurs. In accordance with the statistic data, in 2017, small business is represented by 871 businesses, of which 748 micro-businesses, 64 medium businesses, and 3 large businesses (Appendix B).

The total quantity of entities in Severodonetsk increased dramatically as a result of occupation of a part of Luhansk Oblast. This is explained by changing the regional specialization of Severodonetsk and fulfilling functions of the administrative center of Luhansk Oblast, where some businesses moved from the occupied territory of Luhansk Oblast in 2014–2015. Thus, in 2017, the quantity of entities amounted to 938; the total quantity of persons employed at these entities amounted to 54,309. As compared to 2012, the quantity of entities amounted to 765; the total quantity of persons employed at these entities amounted to 23,426. (Appendix C).

Not only entrepreneurs, but also state, utility, non-government (public) and other entities and organizations moved to Severodonetsk from the occupied territory of Luhansk Oblast. In addition, their quantity in Severodonetsk is increasing gradually from the beginning of military actions. These are 2,563 units as of early 2013, 2,783 in 2015 and 3,203 in 2017.

Most entrepreneursare engaged in production (163 entities) and wholesale/retail trade (335 entities). These types of activities create most jobs in the city.

Large entitiesare engaged in mining industry; medium entities are engaged in transport, warehousing and communication, construction, forestry and fishery sectors, professional, scientific and technical activities, wholesale/retail trade, as well as processing industry. Most small entitiesare engaged in wholesale and retail trade, repair of vehicles, production, real estate operations, construction and professional, scientific and technical activity (Appendix D).

Processing industryis mainly represented by entities engaged in machine building and manufacture of finished steel products, repair of machinery and equipment, and manufacture of clothes, chemicals and plastic goods.

Small and medium businesses rendering the following utility services operate actively in the city: supply of electric power, gas, steam and conditioned air, water supply, sewage, and waste treatment.

The volume of products, goods and services sold by the entities in Severodonetsk increased dramatically to the general regional value after occupation of a part of Luhansk Oblast. In accordance with the statistic data, this share increased from 8.5 % (2012) to 18.5 % (2017). This is explained by the fact that only three industrial cities of regional importance remain within the territory of Luhansk Oblast controlled by the Ukrainian government; the remaining territory is mainly rural (Appendix G).

Results of financial activities of the entities in Sievierodonetsk have deteriorated. Notwithstanding the fact that 71 % of the entities in Severodonetsk were profitable in 2017 as per financial activity results, the remaining 29 % suffered losses. As against 2012, 60 % of the entities were profitable; the remaining 40 % suffered losses. (Appendix J)

The city losses volumes of raised direct investments.So, direct investments (registered capital) amounted to 35.8 % to the general regional value in Severodonetsk in 2017 as against 36.2 % in 2016. This is explained, first of all, by unattractiveness of the city territory for investors due to the proximity to military actions and unfavorable logistic location to the main goods and services sales markets in relation to the regions of Ukraine and abroad (Appendix H).

Foreign trade. In 2017, the foreign trade balance was negative; import dominated export and this repeats the tendency of 2016. The largest share of export is to the following countries: Hungary, Czech Republic, Belarus, Bulgaria, Poland, and France. The largest share of import is from the following countries: France, Poland, Hungary, and Belarus.

Chemical industry in the city diversifies gradually. This has both subjective and objective reasons. Continuous interruptions in operation of the main budget-formation entity – PrJSC “Severodonetsk “Azot” – destabilize the city economy. The military actions in 2014 led to the cease of the entity operation. However, from the end of 2017, the entity has been restoring its operation in the field of “manufacture of main chemical products, fertilizers and nitrogen compounds, plastics and synthetic rubber in primary forms”. As a result, a share of industrial products in this sector of economy sold to processing industry sector in Luhansk Oblast amounted to 20.4 % in June 2018. Nevertheless, the loss of sales markets in the Russian Federation, dependence of process cycles of the entity on expensive resource – natural gas, lack of capital investments in re-equipment of the entity and replacement of production equipment with innovative ones, power supply interruptions made the entity to face interruptions and cease its operation again.

After introduction of the project on 500 kV Kreminska substation construction, the region gained an opportunity for joining the territory of Luhansk Oblast controlled by the Ukrainian government to the territory of the unified energy system of Ukraine, which will enable power supply to PrJSC “Severodonetsk “Azot” and other manufacturing entities in the city. This will be one of favorable factors to resume the entity operation and stimulus to develop SMB around the major budget-formation entity that carries out various types of activities included into links of this entity value added.

Today the most real fact for the city is stable operation of medium and small entities that manufacture rubber and plastic goods, other non-metallic mineral products, which share in processing industry increased systematically from 2014 (0.99 %) to 2017 (3.3 %).

The landmark of Severodonetsk economy is PrJSC “Severodonetsk Research and Production Association “Impulse”. This entity is engaged in “machine building, except repair and installation of machinery and equipment”.

Starting from the Soviet period, Severodonetsk maintains a large number of scientific and research, and design institutes and scientific and production entitiesin the economy structure, which are engaged in scientific and technical developments and engineering that are a perspective field of services for the city; their export share in the structure of foreign trade of services in Luhansk Oblast amounted to 67.5 % in 2017. These services are rendered by medium and small entities, such as PrJSC “Severodonetsk “ORGHIM” (a set of engineering services for process, thermal power, and electrical equipment).

Due to the increase in capital investments in the city infrastructure at the expense of budgetary funds and funds of international beneficiaries in 2014–2017, construction, transport and other logistic services became a perspective sector of economy. In 2017, 3,209 sq. m of total living space were put in operation in the city; this is 4.2 times more than in 2016 (763 sq. m).

Power industry is also a perspective sector of economy. Currently, the city installs boilers powered by alternative fuels, thermal pumps and other power generating units, and individual heating plants in electrical and thermal power boiler houses of budget-funded entities and this saves considerably state funds.

Food industry and agricultural products processing industry have increased their sales volumes for the last three years at the expense of increased population in the city, i. e. sales market. Under conditions of establishment of Sevierodonetsk United Territorial Community, this direction is of top priority due to joined rural territories.

In connection with the fact that Volodymyr Dahl EastUkrainian National University moved to Sevirodonetsk, the city obtained a powerful resource of IT faculty students; therefore, IT is a perspective for the city development under conditions of increasing needs for introduction of e-services in state-owned and municipal organizations in the city, which fulfils functions of the regional administrative center and involves students in entrepreneurial activities in this sector.

Business support infrastructure needs to establish the Local Economic Development Agency as the institution which will ensure consulting, education and information support to business and carry out territorial marketing.

So, the Severodonetsk City Council is responsible for creation of favorable business climate and application of tools for local economic development aimed to maintain and expand existing businesses, and also attract new ones to the city. Such business support will be given by creating high-quality infrastructure for business support and expanding business services, coordinating inter-departmental activity to solve topical issues of business development and staffing, developing utility infrastructure to render high-quality utility services to business, and involving the youth in business sector.

6.2 Inter-sector cooperation and interaction at local level

According to entrepreneurs of the city, the cooperation between state and private sectors is successful. Efficient interaction is between the local government and Economic Development, Trade and Tourism Department, LuhanskOblast Military and Civil Administration, in particular, in the field of regulatory control of entrepreneurial activity; financial and loan, and investment support; resource, information, and staffing support; formation of infrastructure; and innovation project implementation.

The City Council established effective cooperation with Luhansk Regional Chamber of Commerce and Industry on the basis of the created Center for Business Support, which actively arranges round tables, conferences with the participation of entrepreneurs, on issues relating to foreign economic trade, and certification.

The City Council actively cooperates with local economic development institutions, namely Regional Development Agency in Luhansk Oblast, NGO “Luhansk Regional Agency for Development of Communities and Region “Slobozhanschyna”, NGO “Severodonetsk Agency for Community Development”, which actively render information, education, and consulting services to business. Together with the above organizations, the Coordination Council for Business Development was established under the City Council and joint education and information activities are carried out. Together with NGO “Luhansk Regional Agency for Development of Communities and Region “Slobozhanschyna”, the City Council prepared the Severodonetsk Development Strategy until 2020 within the framework of financial support program of the United Nations Development Program. The Agency experts interviewed entrepreneurs, conducted focus groups with entrepreneurs, and developed the Profile of Severodonetsk.

Various advisory and consulting authorities on business issues, namely working groups, community council, advisory council for power efficiency, Coordination Council for Business Development were created under the City Council. Advisory and consulting authorities workactively, prepare road maps of joint activity. This vigorous activity is supported by joint cooperation with international projects, such as GiZ in the field of power efficiency, United Nations Development Program to support business, housing companies, safety, etc.

However, there are problems relating to inter-sector cooperation at local level. The problem lies in the lack of high-quality infrastructure to support business and high-quality services to city business.

There are no horizontal connections and associations of entrepreneurs. It is necessary to establish associations of SMB exporters at local level with further association at all-Ukrainian level.

It is necessary to initiate a constructive dialogue to create and maintain regular contacts of the association of exporters, inter-departmental commissions from among representatives of state authorities, including custom, tax, sanitary-epidemiological, veterinary-sanitary, phytosanitary, environmental, radiological control authorities, city council, as well as non-government institutions to support SMB.

Local economic development institutions mainly raise funds of international beneficiaries to implement territorial development projects; business support is limited to the corresponding term of project implementation and is not systematic.

It is necessary to create a general web-platform to advertise local potential exporters and their products. Estimate of cooperation at local level is outlined in Appendix K.

- 6.3. Transparent, corruption-free administration that encourages business development

The Severodonetsk City Council takes measures aimed at creating favorable business environment for representatives of private sector and civil society. Undoubtedly, the basic prerequisite is a transparent city council.

To ensure transparency and openness, all solutions, measures, social initiatives,projects, regulatory acts, and analytical data on local government activity are published on the official web-site of the Severodonetsk City Council – http://sed-rada.gov.ua/.

To ensure local economic development, it is expedient to enhance transparency of the government by making public information which is critical to business on the web-site of the Severodonetsk City Council: investor roadmap, investment passport of the city, actual rates of city taxes, etc. Development and introduction of the web-portal “Citizen Cabinet”, and also updating of the Sievierodonetsk City Council web-site interface are perspective.

To ensure convenient conditions for rendering services to entrepreneurs and citizens, the Center for Administrative Services operates; it renders 187 administrative services.

In 2018, within the framework of USAIDUCBIII, the automation system and e-turn were introduced in the system of rendering citizens registration/de-registration services. The reception space was updated; comfortable conditions were created for consumers, including disabled persons.

It is planned to expand rooms of CAS and repair additional rooms where passports are issued, increase the number of services for citizens and entrepreneurs (approximately 200).

To fight corruption, the City Council actively takes educational measures for experts of local governments on this issue; an authorized person for corruption prevention and detection in the executive committee of the City Council was assigned by the Order of the Mayor No. 451 dated August 31, 2017. This person carries out its activity in accordance with the Provision approved by the executive committee in 2017.

The official web-site has the section “Corruption prevention” and “Government Purification” where everybody can become familiar with audits of officials, in accordance with the Order of the Mayor No. 240 dated 16.06.2016 “On the start of auditing provided by the Law of Ukraine “On the government purification”. Each citizen can monitor online meetings of the City Council.

The City Council intends to render financial support to business. The Small and Medium Business Development Program in Sievierodonetsk for 2019 was approved by the decision of session No. 3028 dated 09.01.2019, one of which measures is partial compensation under loan agreements to small and medium businesses in Sievierodonetsk at the expense of city budget funds.

The Severodonetsk City Council intends to attract direct investments; to do this, a register of investment proposals was developed in 2015. However, the information is old now and this catalogue should be updated.

To support business, further work of the City Council is required, namely:

- transparent mechanisms of land plot allotment and reduction of rates for manufacturing entities;

- transparent mechanisms of utility property use;

- high-quality administrative services, in particular, e-services;

- financial stimuli to develop business (recovery of loan interests, financial support, etc.);

- support to first-time entrepreneurs (development of business rearers);

- assistance in creating Business Service Centers;

- limitation of access to information;

- city infrastructure development (roads, electric power, water and gas networks).

- 6.4. Access to financing

The financial sector in Severodonetsk is represented by different banks, but only two of them, namely Oschadbank and Privatbank grant loads to small and medium businesses.

However, not enough loans are granted because the banks are careful in estimate of pledged property. They explain this fact that Luhansk Oblast is a territory of risky entrepreneurial activity due to its proximity to the military conflict. Loans are not popular among entrepreneurs either due to the high interest rate on loans (24 % on an average), which makes impossible use of borrowed capital to develop business and increase the quantity of jobs.

Results of entrepreneur interviewing showed that the first problem for entrepreneurial activity is limited cheap financial resources.

The Severodonetsk City Council approved the program of small and medium business development in the city of Severodonetsk for 2018 by the decision of session No, 2534 dated 15.05.2018 and approved the Procedure for Partial Compensation under Loan Agreements to Small and Medium Businesses in the city of Severodonetsk at the expense of local budget funds. Nevertheless, this procedure does not work and partial compensation to entrepreneurs was not provided because of the deferred solving of this solution to 2019.

However, financial and loan support is granted to SMB at the regional level at the expense of bank lending to develop business. Luhansk Oblast Military and Civil Administration promotes such support to top-priority sectors of economy through partial compensation of loan interests from the regional budget. Compensation is granted once, on an irrevocable basis and is aimed at partial compensation of interest rates which were actually paid in the current budget year for loan use. Support is granted in such spheres as introduction of energy saving technologies, centralized water supply and water disposal, introduction of environmental technologies, manufacture of import substitution goods and export oriented goods, etc. Unfortunately, none entity in Sievierodonetsk submitted proposals to gain such support in 2018.

Today, a competition was announced for small and medium businesses within the framework of USAIDDAIERA project to receive grant support to entrepreneurs in such spheres as alternative power engineering, honey production, introduction of IT technologies, innovative production, and vegetable production. Entrepreneurs in Severodonetsk can submit first a project Concept. Then detailed business projects can be developed on the grounds of this Concept.

The Severodonetsk City Council started granting active consulting support to businesses in Severodonetsk on business project development.

Within the framework of this Plan, it is planned to inform businesses about actual opportunities to have access to grant financing on a separate page of the web-site of the Severodonetsk City Council, and also consider an opportunity for restoring the procedure of partial compensation under loan agreements to small and medium businesses at the expense of local budget funds.

- 6.5. Land resources and infrastructure

The analysis of available real estate in Severodonetsk shows the lack of land plots and infrastructure to develop businesses and the free ones do not satisfy the demand (incorrect location or improper size, etc.).

This is a catastrophic situation because the business striving for expansion and investments is concentrated in Severodonetsk; however, the lack of land resources limits opportunities for investors.

Though the city has small land plots and free rooms in large premises which can be used only for micro-business, office rooms, small warehouses, trade entities, household service saloons, and IT specialists, etc., the analysis showed that the need in small land plots, rooms both in free-standing buildings and in buildings with rights of joint use will further increase as a result of increasing population in the city at the expense of IDPs and students. This infrastructure will be mainly used to render services and arrange office rooms.

Small and medium businesses need free land plots with an area exceeding 10 ha, and the city suffers from a lack of such plots. To do this, not only “greenfields”, but also “brownfields” can be used, i. e. plots of ex industrial entities that ceased their activity. These plots have connected utilities which are good to organize production. However, there are weaknesses, namely owners who should agree sale or lease of this land plot.

In 2017, the issue relating to organization of the industrial park operation was considered in the city. Today the issue relating to the park location within the city and land plot determination is being considered. The city has serious limitations to such park arrangement due to the deficit of land plots with an area exceeding 25 ha and more. Nevertheless, this problem can be solved by increasing the city area by joining rural territories and creating the Severodonetsk United Territorial Community, which will increase the city resource. The procedure for joining lands of Borovenky, Iepifanivka, Chabanivka, and Smolianynove Village Councils has been started.

The city has a rather developed engineering and transport infrastructure: no problems with connection to utilities arise, except for connection to power grids. In cases relating to connection to power grids, the municipality is always ready to assist business and becomes a sort of “mediator” in relations between a power company and entity. Considering the city compact size and rather developed transport network, no problems with transport accessibility arise in the city. There is a problem with the bridge connecting the city with the rural territories that intend to join the city.

The City Council also plans to solve the following problems of business provision with land resources and real estate, namely:

- execution of documents and licenses, for example, in relation to land issues, the data from the public cadastral map of Ukraine is incomplete and inaccurate;

- business provision with information about utility non-residential estate: which is leased, which is free, which can be leased or transferred to the ownership;

- creation of land plot registers which can be leased / transferred to ownership, in particular, e-registers.

- 6.6. Legal and institutional base

The city has a municipal regulatory and legal base which regulates activity of businesses at local level. All regulatory acts were adopted in accordance with the requirements set by the Law of Ukraine “On the regulation of economic activity”, in particular, public discussions. In 2018, the applicable regulatory acts adopted by the City Council were updated.

Unfortunately, the business community is almost not involved in discussion of regulatory acts which govern local taxes and duties, but the City Council tries to set optimal tax rates after the fundamental analysis and timely response to changes in the applicable laws or needs of the parties concerned, where applicable.

When initiating or carrying out entrepreneurial activity, the local business faces the following main problems:

- insufficiently effective work of CAS, insufficient interaction between institutions, organizations and utility companies that render services to business, which often forces entrepreneurs to apply themselves to regulatory agencies;

- increase in cost of land plot use (due to considered inflation index when calculating the regulatory monetary estimate of land);

- low level of communication between the government and business when adopting regulatory acts on issues of business, and city development programs;

- insufficient information of business about administrative services, rendering procedures and regulations, available utility property, purchases at the expense of local budget funds, available opportunities for business development, etc.

The existence of these problems results in reduction of entrepreneurial activity decrease. To solve, in part, problems faced by business, it is planned to improve procedures for rendering administrative services for business, in particular, interaction between regulatory authorities; finish filling of the information portal of the city with corresponding information about free land plots and property, services rendered by utility companies and organizations; create an information and consulting portal for business.

The City Council together with entrepreneurs can take a number of measures to solve the problem or decrease its adverse effect and these measures are provided in the MEP Plan.

Problems faced by business circles (acting entrepreneurs and investors) in providing favorable legal and institutional conditions:

- lack of cheap financial and loan resources for business, financial support to business;
limited land resources, real estate and property for business development;

- insufficient level of information and consulting support to entrepreneurs;

- insufficient level of education for entrepreneurs on issues of modern methods and forms of economic management;

- deficit of skilled experts;

- monopoly in connection to power grids.

The Severodonetsk City Council has no register of free land plots and rooms to be used by entrepreneurs and to start or expand entrepreneurial activity. It is necessary to create and make public such registers.

Weak fair and exhibition activity of the city, where an entity or entrepreneur can demonstrate own products for buyer. Weak promotion of production potential of the city at regional and national level. It is necessary to activate this work on the part of the Severodonetsk City Council.

It is necessary to create a local economic development institution – Local Economic Development Agency in Severodonetsk and initiate active consulting, information and education activity for entrepreneurs in the partnership with beneficiaries and other institutions in MEP region.

- 6.7. Skilled labor resources, inclusiveness

Stable operation of small and medium businesses in the field of machine building and steel processing, chemical industry, construction in the city resulted in keeping the tendency for the demand preference to proposition in the employment market. The tendency for deficit of labor resources mainly relates to engineers and technicians, workers (electric fitters, movable equipment repairman, mechanical assemblers, vehicle operators that maintain mechanisms, builders, etc.), and the chemical industry is badly in need for chemical analysts.

Stoppage of the large chemical enterprise (PJSC “Severodonetsk Association “Azot”) resulted in dismissal of about 300 employees, namely managers, professionals, experts, as well as skilled employees. Staffing replacement and levelling of staff deficit in the above sectors of economy can be performed subject to joint work of the local government and local employment center to involve dismissed employees of this enterprise or retrain IDPs moving from the occupied industrial territory of Luhansk Oblast. It is planned to jointly develop the Further Training and Retraining Program which provides for covering the deficit of the above professions and specialities.

The City Council also plans to jointly work with the state educational institution “Luhansk Center of Vocational Education under the State Employment Center”, which was created on the basis of Luhansk Regional Employment Center. The City Council will act as a facilitator of staff selection for business, customized staff training, probation at work, conduct of business trainings, professional training, retraining and further training of staff.

IT industry remains to be of top priority for the city; it faces the deficit of highly skilled programmers, programmer engineers, other specialists in the field of computer technologies due to outflow to other regions of Ukraine and abroad. Further outflow of graduates of Volodymyr Dahl EastUkrainian National University (faculty of information technologies and electronics, department of computer sciences and engineering) is forecast.

Therefore, the City Council plans to activate work with higher education institutions, namely Resource Center for Sustainable Development of Volodymyr DahlEastUkrainian National University where IT faculty students will be able to receive education services for business, training of management staff for business, which will allow them to carry out independent entrepreneurial activity in IT field.

Severodonetsk staff market faces the lack of skilled business trainers, consultants on access to EU markets, foreign economic activity, products certification required by small and medium business.

Within the framework of this Plan, it is expected to create the Local Economic Development Agency which would fulfil functions of rendering education, consulting and information services, including foreign economic activity, certification, as well as training of such consultants for business needs.

- 6.8. External positioning and marketing

The City Council in partnership with public organizations is engaged in marketing of the city territory. Within the framework of the project “Contents of public activity” financed by the European Union, the National Fund to Support Democracy and Polish-American Fund of Freedom undertook a study by deep interviews and focus groups covered by different categories of respondents in the city: from the youth, students and public activists to experienced entrepreneurs, public officers, and pensioners.

As a result, 1,000 questionnaires were collected. The following was marked in positive aspects: 1) reconstructed theatre and adjacent square with fountain;

2) compact size of the city;

3) people that live and lived in the city;

4) green areas in the city (parks, squares, forests, ponds);

5) operating production companies in the city.

Negative aspects include as follows:

1) technical condition of roads and sidewalks;

2) condition of recreation places (squares, parks, stadiums, children's playgrounds);

3) local government (opposition), indifference and inactivity of citizens;

4) unsatisfactory condition of environment (contamination of forests, ponds, adjacent territories).

The initiated active dialogue with the public, entrepreneurs, international beneficiaries, systematic exchange of experience with other regions of Ukraine and abroad within framework of international projects allow the city to build an effective policy to enter national and international markets in cities with successful investments.

This is proved in the following international projects:

Within the framework of the project GiZ “Energy efficiency II”, Severodonetsk became a city mentoring the Eastern Ukraine in terms of energy efficiency.

Within the framework of the project “Transparency and fairness of public sector” supported by the UN Development Program in Ukraine, Severodonetsk is the ninth of 100 largest cities of Ukraine in the rating of investment sector transparency.

This was made possible by participation of the city and its entities in national, regional, international exhibitions and build of consistent participation of entities in such regional exhibitions, such as Business Circle, East – Expo.

This and other initiatives form a positive image of the city, prove its openness and readiness to cooperation.

The City Council plans to continue this work, but on a systematic basis. It is planned to create the Severodonetsk Economic Development Community Agency which would undertake functions of territorial marketing and branding of the city. Today the city has no investment brand and marketing strategy. These documents are extremely necessary for further positioning of the city in the international and national arena as an investment attractive and business comfortable city.

- SWOT analysis

The SWOT analysis for Severodonetsk includes 10 strengths and 7 weaknesses, 7 opportunities and 7 threats:

| Strengths | Weaknesses |
| --- | --- |
| - the city of Severodonetsk – actual status of the regional center of Luhansk Oblast; - diversified sphere of small and medium businesses; - inflow of private entities to the city from the uncontrolled territory of the region, business movement to the city; - export is performed to the following countries: Russian Federation, Hungary, Czech Republic, Belarus, Bulgaria, Poland, and France. The largest import share is from the following countries: Russian Federation, France, Poland, Hungary, and Belarus; - stable medium and small businesses in the field of manufacture of rubber and plastic goods, other non-metallic mineral products, other chemicals, finished metallic goods; - the landmark of Severodonetsk economy is PrJSC “Severodonetsk Research and Production Association “Impulse”; - presence of scientific and research, and design institutes and scientific and manufacturing entities engaged in scientific and technical developments and engineering; - the city installs boilers powered by alternative fuels, thermal pumps and other power generating units, and individual heating plants in electrical and thermal power boiler houses of budget-funded entities; - movement of higher education institutions to the city from the uncontrolled territory of Ukraine, youth inflow; - positive history of cooperation between the city and international beneficiaries; | - lack of full motor and railway service with other regions of Ukraine (due to low capacity of the existing highways); - deteriorated financial activities of entities, negative balance of financial activity and trade; - loss of traditional sales markets by entities in the city; - lack of horizontal connections and associations of entrepreneurs; - difficulties in executing permits and licenses; - outflow of skilled specialists to other regions of Ukraine and abroad; - bureaucracyof advisory and consulting authorities that support entrepreneurs. |
| Opportunities | Threats |
| - completion of the JFO - Partial compensation of interest rates on loans granted to implement projects of small and medium businesses was approved by the Order of the Mayor LOVETS No. 768 dated 26.10.2018; - under conditions of powerful scientific and research institutes and production facilities, it is possible to create a scientific and process fleet on the basis of one or several of them; - presence of technical speciality graduates of Volodymyr Dahl EastUkrainian National University; - increase of land resources in the city by joining adjacent rural territories; - introduction of a project on 550 kV Kreminska substation construction, connection to the unified energy system of Ukraine; - - technical education of the state employment service. | - Ukrainian-Russian conflict in the East Ukraine, proximity to the demarcation; - dependence of process cycles at chemical enterprises on expensive resource – natural gas; - high level of interest rate on loans; - energy dependence on Schastia TPP, no connection to the unified energy system of Ukraine; - technical condition of railway transport is unsatisfactory due to considerable wear of movable assets and main funds; - reversal of reforms that are critical for the state; - unstable political situation and increasing distrust to state government, corruption. |

- Vision and goals

- Vision

Severodonetsk is the administrative center of Luhansk Oblast and potentially united territorial community created by joining adjacent rural communities. Open and safe community of entrepreneurial success in the East of Ukraine, management and production innovations. Intellectual scientific center of “green” technologies, efficient infrastructure and productive employment

- Goals

1. Improving the system of support to local commodity manufacturer and developing new sales markets.

The perspective direction of support to businesses on the part of local development institutions is creation of the Economic Development Agency, business centers and business schools for pupils. To improve the level of knowledge and interest of entrepreneurs, the local development institutions render information, consulting, education and other services.

To promote creation of new and develop efficiently existing small and medium business, it is planned to carry out various activities on the basis of the local economic development institutions to ensure online interaction between entrepreneurial structures and government, promote establishment of public associations of small and medium businesses, and promote development of youth and women's businesses: involvement of entrepreneurs in business forums, round tables, fairs and exhibitions; information in mass media about activities of authorities supporting business, experience in development of small and medium businesses, charity actions of entrepreneurs, and different competitions among entrepreneurs. All this will ensure formation of favorable conditions and public onion and will promote active involvement of population in entrepreneurial activity.

To provide entrepreneurs with high-quality information, it is necessary to provide information of updated databases on free production facilities, trade facilities, restaurants, utility services, water resources and landplots, which can be sold or leased by businesses to carry out entrepreneurial activity.

2. Introducing up-to-date energy performance and energy independence mechanisms in the city.

Energy independence and energy efficiency of the city is formed on the basis of the city policy aimed at formation of infrastructure for renewable power industry, introduction of energy efficient technologies, and effective thermal power supply to the city.

3.Improving competitiveness of citizens due to enlarging land resources and infrastructure security of the city by joining neighbouring rural communities.

The process of marketing strategy formation and introduction will promote formation of new image of the city community as investment attractive one.

It is necessary to form a new positive investment-attractive brand of the city which will have specific advantages. The developed brand will enable “selling” the city to target marketing audiences, in particular, consumers of local resources, goods and services and investors which understand that the city government manages the local environment, makes it more convenient for entrepreneurial activity, and that citizens and potential citizens see opportunities for own self-fulfillment.

One of the most efficient up-to-date strategies of the city image building is city branding composed of two components:

1) city saturation with brand signs that facilitate its marking,

2) process of the city transformation to the brand.

To position the attractiveness of the territory, it is necessary to increase the land resource of the city which faces currently the lack of land resources for a strategic investor. To do this, it is planned to establish the Severodonetsk United Territorial Community using the simplified mechanism of joining rural communities to the Perspective Plan of establishing local communities in Luhansk Oblast: Borivsk, Syrotynsk, Borovenky, Iepifanivka, Smolianynove, Chabanivka, and Myrnolodynsk Village Councils.

To provide the potential UTC with infrastructure, a new modern highway bridge should be constructed across the Borova River, which will join Severodonetsk to Iepifanivka, Borovenky, Smolianynove and Chabanivka.

- Action Plan

Action Plan to implement the Local Economic Development Plan includes 12 actions (Table 1).

Table 1. Action Plan

| Topical unit | Main goals | Action under project(s) | Duration (start/finish) | Partners involved | Estimate expenses, national currency (EUR equivalent) | Result | Monitoring indicators |
| --- | --- | --- | --- | --- | --- | --- | --- |
| - Inter-sector cooperation and interaction at local level - Access to financing Transparent, corruption-free administration that encourages business development External positioning and marketing | 1. Improving the system of support to local commodity manufacturer and developing new sales markets. | 1.1 Establishing the Economic Development Agency in Severodonetsk as a tool of partnership between the government and business | 01.06.2019- 31.12.2019 | Severodonetsk City Council, entrepreneurs | UAH 500,000.00 (EUR 15,559.00) | 1. The Economic Development Agency (EDA) was established and registered. 2. A training program was prepared for entrepreneurs. 3. Training seminars were conducted for entrepreneurs. 4. FEA consulting was introduced. | 1. Registration documents of the EDA. 2. A training program package (6 training modules) was prepared. 3. 6 training seminars were conducted. 4. 180 persons passed training. 5. 30 consultations on FEA were conducted. |
|  |  | 1.2. Restoring the development of the procedure for partial compensation under loan agreements to small and medium businesses at the expense of local budget funds | 01.06.2019- 31.12.2019 | Severodonetsk City Council | UAH 300,000.00 (EUR 9,336.00) | 1. Financing in the amount of UAH 300,000.00 is provided in the local budget for 2019. | 1. The quantity of entrepreneurs that received partial compensation under loan agreements is 10. |
|  |  | 1.3. Creating a modern business center with offices in Open Space format, Smart offices, and conference hall | 01.06.2019- 31.12.2020 | TOV “Promdeks-Ukraine” Severodonetsk City Council | UAH 14,000,000.00 (EUR 435,665.00) | 1. 100 jobs were created. 2. A business space with a capacity of 5,000 persons per months was created. | 1. The quantity of new jobs is 100. 2. The modern space with a conference hall and training rooms (5 rooms) was equipped. |
|  |  | 1.4. Creating an innovative educational program for school-aged children “I am a successful person” was created. | 01.06.2019- 31.12.2020 | International School of Innovative Education “Rainbow”, branch office in Severodonetsk | UAH 300,000.00 (EUR 9,336.00) | 1. Trainings for children, master classes with the participation of successful businessmen and entrepreneurs of the city ready to tell about own experience were conducted. 2. “Marathon of Professions” was conducted; it will allow pupils to choose profession in a more deliberate manner. 3. Tournaments, competitions of business projects were conducted to encourage the youth to study and achieve own dreams, goals, etc. | 1. The quantity of trainings / competitions / tournaments is 10. 2. The quantity of developed business projects is 10. 3. The quantity of participants in each action is 50. |
|  |  | 1.5 Creating an agricultural hub | 01.06.2019- 31.12.2020 | TOV “UKRKHIMEXPORT” Severodonetsk City Council | UAH 15,000,000.00 (EUR 466,784.00) | 1. Warehouses were opened. 2. Prepacking and packing services were rendered (fertilizers, chemicals for plant protection, seeds). | 1. The warehouse area is 300 sq. m. |
|  |  | 1.6. Creating a youth sport and entertainment Center of Activity | 01.06.2019- 31.12.2020 | Severodonetsk City Council, entrepreneurs | UAH 16,577,000.00 (EUR 515,859.00) | 1. AN open unique facility representing a stadium with a set of sports grounds located in 49a quarter in Severodonetsk was created. | 1. 15 new jobs. 2. 30 sport events per year. 3. 400 participants of sport and cultural events. |
|  |  | 1.7. Developing a brand and marketing strategy of the city | 01.06.2020- 31.12.2020 | Severodonetsk City Council | UAH 100,000.00 (EUR 3,112.00) | 1. The brand was developed: logo, slogan, and brand book. 2. The marketing strategy was developed. 3. Promotion materials about the city were created. | 1. A working group for the marketing strategy development was created. 2. 4 meetings of the working group were conducted. |
| - Inter-sector cooperation and interaction at local level Land resources and infrastructure Transparent, corruption-free administration that encourages business development | 2. Introducing up-to-date energy performance and energy independence mechanisms in the city. | 2.1. Constructing facilities to manufacture briquettes from vegetative stock, with a capacity of 2,200 t of briquettes per year | 01.06.2019- 31.12.2020 | TOV “Engineering investment company “Teploenergoservis” Severodonetsk City Council | UAH 4,000,000.00 (EUR 124,476.00) | 1. Facilities to manufacture briquettes from vegetative stock were constructed. 2. Solid fuel operated boiler houses are provided with high-quality cheap fuel. | 1. 2,200 t of high-quality biofuel are manufactured a year. 2. 40 new jobs were created. |
|  |  | 2.2. Constructing five self-contained solid fuel operated boiler houses for general education and pre-school educational institutions in Sievierodonetsk | 01.06.2019- 31.12.2020 | TOV “Ekotekh” Severodonetsk City Council | UAH 15,630,000.00 (EUR 486,389.00) | 1. Five self-contained solid fuel operated boiler houses were constructed. 2. Alternative fuels are used to produce thermal power. | 1. 5 self-contained solid fuel operated boiler houses were installed in educational and pre-school institutions in the city. 2. 50 new jobs. 3. The natural gas consumption was reduced by 675 thousand m3 per year. |
|  |  | 2.3. Installing IHPs in budget-funded institutions and creating a service company (5 schools) | 01.06.2019- 31.12.2020 | Severodonetsk City Council | UAH 1,500,000.00 (EUR 46,678.00) | 1. 5 IHPs were installed in the schools in the city. 2. A IHP service company was created. | 1. 10 new jobs were created. 2. 5 IHPs were installed in the schools in the city. |
| - Inter-sector cooperation and interaction at local level Land resources and infrastructure Transparent, corruption-free administration that encourages business development | 3.Improving competitiveness of citizens due to enlarging land resources and infrastructure security of the city by joining neighbouring rural communities. | 3.1. Joining rural communities and increasing the land resource of the city | 01.06.2019- 31.12.2019 | Severodonetsk City Council, Iepifanivka, Chabanivka, Smolianynove, Borovenky, and Myrnodolynsk Village Councils | UAH 30,000.00 (933.6) | 1. The Severodonetsk City UTC was created by joining Iepifanivka, Chabanivka, Smolianynove, Borovenky, and Myrnodolynsk Village Councils to the Severodonetsk City Council | 1. 5 village councils were joined. 2. 31.83 km2 of land were additionally joined. |
|  |  | 3.2. Constructing a new modern highway bridge across the Borova River | 01.06.2019- 31.12.2020 | Severodonetsk City Council, Rubizhne City Council | UAH 60,000,000.00 (EUR 1,867,138.00) | Continuous and safe traffic between Severodonetsk and Rubizhne was provided; two-way traffic was launched between the cities | A modern highway bridge across the Borova River, which was destructed during the ATO in 2014, was constructed. |

Financing scheme

The total amount of financing of all project activities is UAH 127,937.00 thousand (EUR 3,981.267 thousand). It is planned tofinance 7 % of the total amount using the local budget funds, 63 % using beneficiaries' funds, 16 % using top level budgets, and 14 % using private sector funds. (Table 2).

Table 2. Financing scheme

| Actions | Planned expenses, UAH/EUR | Sources of financing, UAH/EUR |  |  |  | Lack of financing, UAH/EUR | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Local budget | Top level budgets | Private sector | Beneficiaries |  |  |
| 1.1 Establishing the Economic Development Agency in Severodonetsk as a tool of partnership between the government and business | 500,000.00/ 15,559.00 | - | - | 50,000.00/ 1,556.00 | 450,000.00/ 14,003.00 | - | - |
| 1.2. Restoring the development of the procedure for partial compensation under loan agreements to small and medium businesses at the expense of local budget funds | 300,000.00/ 9,336.00 | 300,000.00/ 9,336.00 | - | - | - | - | - |
| 1.3. Creating a modern business center with offices in Open Space format, Smart offices, and conference hall | 14,000,000.00/ 435,665.00 | 1,000,000.00/ 31,119.00 | - | 7,000,000.00/ 217,832.00 | 6,000,000.00/ 186,714.00 | - | - |
| 1.4. Creating an innovative educational program for school-aged children “I am a successful person” was created. | 300,000.00/ 9,336.00 | - | - | - | 300,000.00/ 9,336.00 | - | - |
| 1.5 Creating an agricultural hub | 15,000,000.00/ 466,784.00 | - | - | 7,000,000.00/ 217,832.00 | 8,000,000.00/ 248,952.00 | - | - |
| 1.6. Creating a youth sport and entertainment Center of Activity | 16,577,000.00/ 515,859.00 | 1,000,000.00/ 31,119.00 | - | 2,000,000.00/ 62,238.00 | 13,577,000.00/ 422,502.00 | - | - |
| 1.7. Developing a brand and marketing strategy of the city | 100,000.00/ 3,112.00 | 50,000.00/ 1,556.00 | - | - | 50,000.00/ 1,556.00 | - | - |
| 2.1. Constructing facilities to manufacture briquettes from vegetative stock, with a capacity of 2,200 t of briquettes per year | 4,000,000.00/ 124,476.00 | - | - | 1,000,000.00/ 31,119.00 | 3,000,000.00/ 93,357.00 | - | - |
| 2.2. Constructing five self-contained solid fuel operated boiler houses for general education and pre-school educational institutions in Severodonetsk | 15,630,000.00/ 486,389.00 | 2,000,000.00/ 62,238.00 | - | 630,000.00/ 19,605.00 | 13,000,000.00/ 404,546.00 | - | - |
| 2.3. Installing IHPs in budget-funded institutions and creating a service company (5 schools) | 1,500,000.00/ 46,678.00 | 200,000.00/ 6,224.00 | - | - | 1,300,000.00/ 40,454.00 | - | - |
| 3.1. Joining rural communities and increasing the land resource of the city | 30,000.00/ 933.6 | - | - | - | 30,000.00/ 933.6 | - | - |
| 3.2. Constructing a new modern highway bridge across the Borova River | 60,000,000.00/ 1,867,138.00 | 4,000,000.00/ 124,476.00 | 21,000,000.00/ 653,498.00 | - | 35,000,000.00/ 1,089,164.00 | - | - |
| Total | 127,937,000.00/ 3,981,266.8 | 8,550,000.00/ 266,067.00 | 21,000,000.00/ 653,498.00 | 17,680,000.00/ 550,183.00 | 80,707,000.00/ 2,511,518.1 | - | - |

11. Monitoring indicators and mechanisms

Table 3. Monitoring indicators and mechanisms

| Actions / Ideas of project(s) | Duration (start of action (dd.mm.yyyy – finish dd.mm.yyyy) | Expected results |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | from 6th to 9th month | from 10th to 12th month | from 13th to 18th month | from 19th to 24th month |
| 1.1 Establishing the Economic Development Agency in Severodonetsk as a tool of partnership between the government and business | 01.06.2019- 31.12.2019 | Registration documents were received. A training program package (6 training modules) was prepared. 3 training seminars were conducted for entrepreneurs. | 3 training seminars were conducted. 30 consultations on FEA were conducted. | - | - |
| 1.2. Restoring the development of the procedure for partial compensation under loan agreements to small and medium businesses at the expense of local budget funds | 01.06.2019- 31.12.2019 | UAH 300 000 are provided in the local budget for 2019. | Partial compensation under loan agreements was granted to 10 entrepreneurs. | - | - |
| 1.3. Creating a modern business center with offices in Open Space format, Smart offices, and conference hall | 01.06.2019- 31.12.2020 | - | Rooms for the business center were selected and equipped. | The modern space with a conference hall and training rooms (5 rooms) was equipped. The quantity of new jobs is 100. | - |
| 1.4. Creating an innovative educational program for school-aged children “I am a successful person” was created. | 01.06.2019- 31.12.2020 | The quantity of trainings / competitions / tournaments is 2. | The quantity of trainings / competitions / tournaments is 3. The quantity of developed business projects for the competition is 10. | The quantity of trainings / competitions / tournaments is 2. | The quantity of trainings / competitions / tournaments is 3. |
| 1.5 Creating an agricultural hub | 01.06.2019- 31.12.2020 | - | Documents for the land plot were selected and executed. | Warehouses with an area of 300 m2 were built. | Package production was started (500 kg per year). |
| 1.6. Creating a youth sport and entertainment Center of Activity | 01.06.2019- 31.12.2020 | Bids to define the stadium construction winner were conducted. | Stadium construction was started. | A sport and entertainment facility with sport grounds were created and put into service. | 30 sport and entertainment events were conducted. 15 new jobs were created. |
| 1.7. Developing a brand and marketing strategy of the city | 01.06.2020- 31.12.2020 | - | - | A working group for the marketing strategy development was created. 4 meetings of the working group were conducted. | The marketing strategy and brand of the city were developed. Promotion materials about the city were issued. Souvenirs were given. |
| 2.1. Constructing facilities to manufacture briquettes from vegetative stock, with a capacity of 2,200 t of briquettes per year | 01.06.2019- 31.12.2020 | - | Manufacture of briquettes from vegetative stock was started. | A facility manufacturing briquettes from vegetative stock with a capacity of 2,200 t was constructed and put into service. | Production of high-quality biofuel, 2,200 t per year. 40 new jobs were created. |
| 2.2. Constructing five self-contained solid fuel operated boiler houses for general education and pre-school educational institutions in Severodonetsk | 01.06.2019- 31.12.2020 | - | Construction of five self-contained solid fuel operated boiler houses was started. | Five self-contained solid fuel operated boiler houses were constructed and put into service. | The natural gas consumption was reduced by 675 thousand m3 per year. 5 schools and pre-school institutions receive high-quality thermal power. 50 new jobs were created. |
| 2.3. Installing IHPs in budget-funded institutions and creating a service company (5 schools) | 01.06.2019- 31.12.2020 | - | 3 IHPs were installed in the schools in the city. | 2 IHPs were installed in the schools in the city. | A servicecompany was established; 10 new jobs were created. |
| 3.1. Joining rural communities and increasing the land resource of the city | 01.06.2019- 31.12.2020 | - | Corresponding decisions were made by the council sessions. | 31.83 km2 of land were additionally joined. | - |
| 3.2. Constructing a new modern highway bridge across the Borova River | 01.06.2019- 31.12.2020 | Bids to define the bridge construction winner were conducted. | Construction of a new modern highway bridge across the Borova River was started. | A new modern highway bridge across the Borova River was constructed. | Road junction was made near the newly built bridge across the Borova River. |
| % of total budget for all MEP plan actions (approximately) | UAH 127,907,000.00 (EUR 3,980,333.00) | 7 % | 16 % | 14 % | 63 % |

To monitor implementation of the Local Economic Development Plan in Severodonetsk, the working group for the Plan development created a Plan Implementation Monitoring Committee. The Committee was composed of three persons: one representative from the executive committee, business and public organization. It is planned to conduct meetings of the Committee in the second Thursday of the quarter following the accounting one.

Persons responsible for carrying out the Plan actions shall submit reports on carrying out actions not later than on 10.07.2019, 10.01.2020, 10.07.2020 and 10.01.2021 to the Plan Implementation Monitoring Committee.

Based on results of the Plan Implementation Monitoring Committee meetings, it is planned to prepare semi-annular Reports on the Local Economic Development Plan Implementation, send them to the national office of the Initiative “Measures for Economic Development” and publish them on the web-site of the Severodonetsk City Council.

- Appendix 1.

- одаток 2.

- Додаток 2.

- Додаток A. Процес розробки Плану місцевого економічного розвитку

- Додаток A. Процес розробки Плану місцевого економічного розвитку

The Local Economic Development Plan was developed on the basis of the following main principles:

| Partnership | Conducting various consultations, discussions, agreements aimed at consensus building in the community. All the parties concerned were invited to participate in approval of solutions and development of the Local Economic Development Plan, namely representatives of the government, scientific institutions, associations of entrepreneurs, entities and entrepreneurs, and representatives of the civil society. |
| --- | --- |
| Resiliency | Planning real sources of financing and volumes of financing |
| Integration | Інтеграція, як багатомірний план розвитку пріоритетних секторів і напрямків діяльності, забезпечує усунення конфліктів та негативних впливів, а також забезпечує зосередження на сумісності та синергії заходів. Integration is ensured by active participation of all the parties concerned. |
| Innovation | Застосовується як принцип у процесі ідентифікації проектів, і стосується, головним чином, запропонованого підходу та як найефективнішого використання наявних ресурсів |
| Institutional memory | It is based on results received during development of previous strategic documents |
| Subsidiarity | Strategic measures starting from the lowest level (based on the community needs) were identified using local economic development resources |

Actions were performed at six stages during the Local Economic Development Plan development:

| 1) Planning work arrangement. | 4) Розробка планів дій. |
| --- | --- |
| 2) Local economic structure analysis. | 5) Public discussion and approval of the Plan. |
| 3) Identification of strategic vision, goals. | 6) Моніторинг і впровадження Плану. |

- SWOT-аналіз

- Стратегічне Бачення

- Goals

- Планидій

- Проектитазаходи

Аналіз

- Аналізструктуримісцевоїекономіки

- Аналіз кожного з тематичнихблоківІніціативи «Мери за економічнезростання»

- Громадськеобговорення

- Ухваленняміськоюрадою

- Моніторингіоцінка

Планування

Впровадження

- Етап 1: Організація роботи

Розпорядженням міського голови від 20 липня 2018 року № 197 було затверджено склад Робочої групи із розробки «Плану місцевого економічного розвитку міста Сєвєродонецька» в рамках Ініціативи ЄС «Мери за економічне зростання» у кількості 18 осіб. Саме на засіданнях Робочої групи були презентовані, обговорювались усі напрями роботи та ухвалювались відповідні рішення. Склад РГ сформований із: представників органів місцевого самоврядування, приватних компаній та підприємців,громадських організацій. Створення саме такого типу партнерства стає вагомим чинником, який підвищує якість та цінність кінцевих матеріалів і зміцнює ймовірність того, що проекти, які включено до Плану будуть впроваджені, а цілі, визначені у ньому будуть реалізовані.

The Plan development schedule became the main tool of planning process management.

- Етап 2: Local economic structure analysis

Аналіз місцевої економічної структури включив в себе:

- Аналіз структури місцевої економіки.

- Аналіз кожного з тематичних блоків Ініціативи «Мери за економічне зростання».

Аналіз структури місцевої економіки (об’єктивний аналіз) проведено на підставі статистичних даних щодо видів компаній за розміром і видами діяльності, показників за минулий рік і тенденцію останніх кількох років.Це надало можливостей визначити найбільш перспективні галузі, що мають потенціал для зростання.

Аналіз кожного з тематичних блоків Ініціативи «Мери за економічне зростання» (суб’єктивний аналіз) здійснено на підставі анкетування підприємців та менеджерів підприємств.

Тематичні блоки, які проаналізовано:1) міжсекторальна співпраця та взаємодіяна місцевому рівні; 2) прозора, вільна від корупції адміністрація, що сприяє розвитку бізнесу; 3) земельні ресурси та інфраструктура; 4) доступ до фінансування; 5) зовнішнє позиціювання та маркетинг; 6) кваліфіковані трудові ресурси, інклюзивність; 7) правова та інституціональна база.

Аналіз всіх тематичних блоків базувався на результатах опитування 25 підприємців та представників підприємств міста Сєвєродонецька. Дане опитування відноситься до формату експертного і не представляє собою соціалогічне опитування. Вибірка опитаних респондентів не відображає сто відсотків структуру місцевої економіки, а лише зріз частини місцевої економіки міста. Опитування відбувалось шляхом інтерв’ювання респондентів, а також занесення даних анкети в онлайн-режимі на офіційному сайті міської ради. Анкета включила в себе дані, інформацію, досвід, а також точки зору представників приватного сектора. Результати та висновки, отримані в результаті цього аналізу, представлені в Плані та стали основою рішень на користь вибору певних дій серед можливих варіантів.

Розробка SWOT-аналізу

Для отримання більш повного уявлення про економічну ситуацію проведено розширений SWOT-аналіз місцевої економіки. SWOT-аналіз (сильні, слабкі сторони, можливості, загрози) проведено за темою «Зростання, розвиток, зайнятість» з фокусом на приватний сектор і його потенціал до зростання, створення можливостей для працевлаштування та нарощування ресурсів для розвитку.

- Етап 3: Визначення бачення, цілей

Третій етап покликаний завершити процес планування місцевого економічного розвитку, що відповідає звичайній практиці і принципам подібного планування.На цьому етапі Партнерство в інтересах місцевого економічного розвитку погоджує своє бачення і цілі, а потім визначає заходи, які вживатимуться відповідно до проаналізованих та прийнятих в роботу тематичних блоків.

Бачення є зрозумілим і підтримується всіма членами громади; має широке охоплення і враховує різні місцеві інтереси; надихає і мотивує всіх, хто бере участь в плануванні.

Основні цілі вказують на конкретні результати, досягнення яких прагне місцеве співтовариство. Вони поглиблюють бачення, а також дають розуміння того, яким чином воно буде реалізоване.

- Етап 4: Розробка планів дій

Докладний план дій є невід'ємною частиною Плану місцевого економічного розвитку та ключовою вимогою для його подальшого успішного здійснення. Кожна потенційна дія в рамках місцевого економічного розвитку відповідає загальному баченню і цілям місцевого економічного розвитку, які обговорювалися і були узгоджені зацікавленими сторонами.

У План дій включені  тільки ті заходи, які вважаються здійсненними.

- Етап 5: Громадське обговорення та ухвалення Плану

Склавши План місцевого економічного розвитку, РГ ініціювала проведення громадського обговорення. Після проведення громадського обговорення допрацьовані проекти документів подавалися на розгляд і ухвалення міській раді в якості політики міста.

- Етап 6: Моніторинг і впровадження Стратегії

Система моніторингу включає: орган з моніторингу (Комітет з моніторингу); документ (Положення) про систему моніторингу виконання Плану з місцевого економічного розвитку (засідання Комітету раз на квартал); систему індикаторів (результатів) виконання Плану місцевого економічного розвитку (кількісні та якісні показники / індикатори).

- Додаток B. Класифікація підприємств за розміром

Table 4. Класифікація підприємств за розміром (згідно Господарського Кодексу України)

| Тип | Кількість одиниць |
| --- | --- |
| Малий бізнес, з них | 871 |
| Мікро-бізнез (приватний підприємець) | 748 |
| Середній бізнес | 64 |
| Великий бізнес | 3 |
| Усього | 938 |

- Додаток C. Класифікація за видами економічної діяльностіта кількість найманих працівників

Таблиця 5.Класифікація суб’єктів господарювання м. Сєвєродонецькк за видами економічної діяльностіта кількість найманих працівників

| Видидіяльності | Кількістьпідприємств, одиниць | Кількістьнайманихпраціників, осіб | У тому числі |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Великіпідприємства |  | Середніпідприємства |  |
|  |  |  | осіб | % до загальної кількості | осіб | % до загальної кількості |
| Усього | 67 | 34614 | 17076 | 49.3 | 17538 | 50.7 |
| Лісове та рибне господарство | 3 | 1935 |  |  | 1935 | 100.0 |
| Будівництво | 5 | 980 |  |  | 980 |  |
| Оптова та роздрібна торгівля, ремонт автотранспортніх засобів і мотоциклів | 17 | 2610 |  |  | 2610 |  |
| Транспорт, складське господарство, поштова та кур’єрська діяльність | 6 | 986 |  |  | 986 |  |
| Тимчасове розміщування та організація харчування | 2 | 1 |  |  | 1 |  |
| Опрації з нерухомиммайном | 2 | 1 |  |  | 1 |  |
| Професійна, наукова, та технічнадіяльність | 5 | 1596 |  |  | 1596 |  |
| Діяльність у сферіадміністративного та допоміжногообслуговування | 1 | 1 |  |  | 1 |  |
| Промисловість | 26 | 25950 | 17076 | 65.8 | 8874 | 34.2 |
| у тому числі |  |  |  |  |  |  |
| Добувна промисловість і розроблення кар’єрів | 3 | 2426 |  |  | 2426 | 100.0 |
| Переробна промисловість | 17 | 20846 |  |  |  |  |
| Виробництво одягу, шкіри, виробів зі шкіри та інших матеріалів | 1 |  |  |  |  |  |
| Виробництво хімічних речовин і хімічної продукції | 4 | 4622 |  |  |  |  |
| Виробництво гумових та пластмасових виробів, іншої неметалевої мінеральної продукції | 2 |  |  |  |  |  |
| Виробництво готових металевих виробів, крім машин та устаткування | 2 |  |  |  |  |  |
| Машинобудування | 7 | 4157 |  |  | 4157 | 100.0 |
| Виробництво комп’ютерів, електронної та оптичної продуції | 2 |  |  |  |  |  |
| Виробництво машин і устаткування | 2 |  |  |  |  |  |
| Виробництво автотранспортних засобів, причепів і напівпричепів та інших транспортних засобів | 3 | 2957 |  |  | 2957 | 100.0 |
| Ремонт, монтаж машин і устаткування | 1 |  |  |  |  |  |
| Постачання електроенергії, газу, пари та кондиційованого повітря | 4 | 2323 |  |  |  |  |
| Водопостачання, каналізування, поводження з відходами | 2 |  |  |  |  |  |

Fig. 2 Structure of Sievierodonetsk economy by number of entities

Додаток D. Розподіл компаній приватного сектору за чисельністю та видами діяльності

Table 6. Breakdown of private entities in Sievierodonetsk by number and types of activities

|  | Кількість підприємств, одиниць |  |  |  | Всього |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Великі | Середні | Малі | З них мікро-підприємства | Кількість (одиниць) | У % до загальної кількості підприємств відповідного виду діяльності |
| Сільське, лісове та рибне господарство | - | 3 | 5 | 4 | 8 | 0.9 |
| Промисловість | 3 | 23 | 137 | 108 | 163 | 17.4 |
| Будівництво | - | 5 | 93 | 76 | 98 | 10.5 |
| Оптова та роздрібна торгівля; ремонт автотранспортних засобів і мотоциклів | - | 17 | 318 | 287 | 335 | 35.7 |
| Транспорт, складське господарство, поштова та кур’єрська діяльність | - | 6 | 31 | 26 | 37 | 3.9 |
| Тимчасове розміщування й організація харчування | - | 2 | 11 | 6 | 13 | 1.4 |
| інформація та телекомунікації | - | - | 30 | 24 | 30 | 3.2 |
| Фінансова та страхова діяльність | - | - | 3 | 2 | 3 | 0.3 |
| Операції з нерухомим майном | - | 2 | 86 | 80 | 88 | 9.4 |
| Професійна, наукова та технічна діяльність | - | 5 | 67 | 54 | 72 | 7.7 |
| Діяльність у сфері адміністративного та допоміжного обслуговування | - | 1 | 34 | 31 | 35 | 3.7 |
| Освіта | - | - | 5 | 4 | 5 | 0.5 |
| Охорона здоров’я та надання соціальної допомоги | - | - | 28 | 24 | 28 | 3.0 |
| Мистецтво, спорт, розваги та відпочинок | - | - | 3 | 3 | 3 | 0.3 |
| Надання інших видів послуг | - | - | 20 | 19 | 20 | 2.1 |
| Разом: | 3 | 64 | 871 | 748 | 938 | 100.0 |

Додаток G. Volume of sold industrial products

Table 8. Volume of sold industrial products

|  | Volume of sold industrial products (товарів, послуг) без ПДВ та акцизу |  |
| --- | --- | --- |
|  | тис.грн. | у % до всієїреалізованої продукції |
| - Луганська область1 | 23244764.2 | 100.0 |
| Місто – конкурент м.Лисичанськ | 1138282.3 | 4.9 |
| Місто – конкурент м.Рубіжне | 6149316.4 | 26.5 |
| м.Сєвєродонецьк | 4288867.3 | 18.5 |

1Без урахування частини зони проведення антитерористичної операції.

Додаток Н. Direct investments (registered capital)

Table 9. Direct investments (registered capital)

|  | Обсяги інвестицій на |  |  |  |
| --- | --- | --- | --- | --- |
|  | 01.01.2017р. |  | 31.12.2017р. |  |
|  | тис.дол. США | у % дозагального підсумку | тис.дол. США | у % дозагального підсумку |
| Луганська область | 436441.7 | 100.0 | 441538.9 | 100.0 |
| Місто – конкурент м.Лисичанськ | 122494.1 | 28.1 | 119585.5 | 27.1 |
| Місто – конкурент м.Рубіжне | 10899.2 | 2.5 | 9896.8 | 2.2 |
| м.Сєвєродонецьк | 158175.0 | 36.2 | 157894.7 | 35.8 |

Додаток I. Volumes of exported – imported services

Таблиця 10.Обсяги експорту – імпорту послуг

|  | Експорт |  | Імпорт |  |
| --- | --- | --- | --- | --- |
|  | вартість, тис.дол.США | відсотків дозагального обсягуекспорту | вартість, тис.дол.США | відсотків дозагального обсягуекспорту |
| Луганська область | 9951.7 | 100.0 | 55211.7 | 100.0 |
| Місто – конкурент м.Лисичанськ | - | - | 26400.1 | 47.8 |
| Місто – конкурент м.Рубіжне | 274.1 | 2.8 | 16390.8 | 29.7 |
| м.Сєвєродонецьк | 9193.3 | 92.4 | 11891.1 | 21.5 |

Додаток J. Pre-tax financial results of entities

Table 11. Pre-tax financial results of entities

(тис.грн)

|  | Фінансовий результат (сальдо) | Підприємства, які одержали прибуток |  | Підприємства, які одержали збиток |  |
| --- | --- | --- | --- | --- | --- |
|  |  | у % до загальної кількості підприємств | фінансовий результат | у % до загальної кількості підприємств | фінансовий результат |
| Луганська область | -25783260.2 | 78.8 | 3822791.7 | 21.2 | 29606051.9 |
| м.Сєвєродонецьк | -24039011.8 | 71.0 | 1085039.5 | 29.0 | 25124051.3 |

Додаток K. Estimate of cooperation at local level

Таблиця 12.Оцінка співпраці на місцевому рівні

| Назва та/або функція (сфера/тема якої вона стосується) | Залучені інституції/ особи | Досягнення (тут також потрібно вказати, яким чином вона здійснюється: наприклад, на етапі планування, реалізації проектів, надання послуг, на постійній основі або періодично/ разово) | Оцінка: корисно чи не корисно |
| --- | --- | --- | --- |
| Співпраця «Регіональний орган влади – ОМС – бізнес» | # Департамент економічного розвитку, торгівлі та туризму Луганської обласної військово-цивільної адміністрації | Організаційні. визначення пріоритетів регіону враховуючи його особливості щодо розвитку малого бізнесу та створення сприятливого середовища для нього; розробка регіональної програми розвитку малого бізнесу; підготовка та перепідготовка кадрів; інформаційне науковометодичне, консультаційне забезпечення; пропагандистська робота; міжрегіональна співпраця. Правові. Розпорядження голови ВЦА у сфері оподаткування, рівень, ставки та механізм збирання місцевих податків та зборів з суб’єктів малого бізнесу; про пільги, субсидії, дотації, порядок цільового фінансування. Економічні. Запровадження механізму регіональних замовлень; створення ринкової інфраструктури, яка б стимулювала розвиток малого бізнесу; розробка гнучкої системи застосування фінансових механізмів підтримки малого бізнесу; інноваційна підтримка, застосування пільг для тих, хто займаються інноваційною діяльністю Види підтримки: впорядкування нормативного регулювання підприємницької діяльності, фінансово-кредитна та інвестиційна підтримка, ресурсне, інформаційне, кадрове забезпечення, формування інфраструктури, інноваційні проекти. | Корисно |
| Співпраця «ОМС – бізнес» | Управління/відділи економіки міських рад | Організаційні. Визначення пріоритетних напрямів розвитку малого підприємництва на рівні міста; встановлення режиму використання об'єктів нерухомого майна та використання і забудови земель; розробка програми розвитку малого бізнесу; розробка і впровадження механізму передачі або надання в оренду малим підприємствам виробничих площ, обладнання, земельних ділянок; інформаційна, консультаційна підтримка; пропаганда; максимальне спрощення процесу реєстрації, видачі дозволів. Економічні. Розробка та запровадження механізму оподаткування щодо місцевих податків | Корисно |
|  | ЦНАП (Центр надання адміністративних послуг) | Адміністративні послуги у сфері державної реєстрації юридичних осіб та фізичних осіб – підприємців; державної реєстрації речових прав на нерухоме майно; послуги Державної служби України з питань геодезії, картографії та кадастру | Корисно |
|  | Дорадчо – консультативні органи | Робочі групи, Громадська рада, Дорадча раза з питаь енергоефективності, Координаційна рада з питань розвитку підприємництва | Корисно |
| Співпраця «Сліужба зайнятості – ОМС – підприємництво» | Державнийнавчальний заклад «Луганський центр професійно-технічноїосвітидержавноїслужбизайнятості» | - Підбірперсоналу - Навчанняпідзамовлення - Стажуваннянаробочомумісці - Бізнес-тренінги Професійнапідготовка, перепідготовка і підвищеннякваліфікації персоналу | Корисно |
|  | Луганський обласний центр зайнятості | Здійснення інформаційно-консультаційного супроводу підприємців під час їх участі у грантових програмах різної спрямованості Підвищення якості бізнес-планів, підготовки відеоуроків і вебінарів з бізнес-планування та подальших стратегій започаткування і ведення підприємницької діяльності | Корисно |
| Співпраця «ОМС – НУО – бізнес» | # Сєвєродонецький Фонд підтримки підприємництва | Фінансова підтримка Бізнес-навчання Стартапи і трансфер технологій | Корисно |
|  | Луганська регіональна торгово- промислова палата | Центр підтримки підприємництва: Лобіювання інтересів підприємництва, зокрема надання можливості організації прямого діалогу підприємництва і влади шляхом участі суб'єктів підприємницької діяльності в різного роду широкомасштабних представницьких заходах: організація конференцій; лобіювання інтересів за допомогою участі в роботі спеціалізованих комітетів ТПП; організація засідань круглих столів та різних громадських слухань. | Корисно |
|  | Агенція регіонального розвитку Луганської області | Організаційні та юридичні послуги Освітні та інформаційні послуги Дослідницькі та аналітичні послуги Стратегічне планування Юридичний та технічний супровід інвестора | Корисно |
|  | ГО «Луганська обласна агенція розвитку громад та регіону «Слобожанщина» | Освітні та інформаційні послуги для підприємництва, ОМС Дослідницькі та аналітичні послуги Стратегічне планування Супровід інвестиційної діяльності Проектний менеджмент Консультаційні послуги Конференс-сервіс | Корисно |
|  | Агентство стійкогорозвиткуЛуганськогорегіону | - Бізнес-планування - Аналіз ринку та проведеннямаркетинговихдосліджень - Юридичнадопомога | Корисно |
|  | Агентство регіонального розвитку Східного Донбасу | Навчальні програми та тренінги; Інформаційна та комунікаційна підтримка; Консультаційна та юридична підтримка; Збір,обробка та поширення інформації Консультаційні послуги та посередництво Маркетингові та інші дослідження Розробка бізнес-планів і проектів | Корисно |
|  | Місцевий осередок територіального відділення Всеукраїнської громадської організації «Асоціація платників податків України» в Луганській області в м.Сєвєродонецьку | Лобіювання інтересів суб’єктів підприємницької діяльності Організаційні послуги Освітні послуги | Корисно |
|  | ГО «Сєвєродонецька молодіжна рада» | Мікро-гранти для жіночого підприємництва Освітні послуги | Корисно |
| Співпраця «ОМС – ВНЗ – бізнес» | Ресурсний Центр зі сталого розвитку Східно-Українськогонаціональногоуніверситетуім. Volodymyr Dahl Даля | Освіта для бізнесу, наукові розробки та дослідження для бізнесу, партнерство між бізнесом і владою, організаційні послуги | Корисно |
|  | Східноукраїнський національний університетім. Даля (СНУ) ПТУ | Освіта для бізнесу | Корисно |
| «Співпраця фінансова організація – бізнес» | Філія відділення публічного акціонернерного товариства «Промінвестбанку» | Кредитуванняпідприємств малого та середньогобізнесу | Корисно |
|  | Філія акціонерного комерційного інноваційного банку «Украсиббанк» | Кредитуванняпідприємств малого та середньогобізнесу | Корисно |
|  | Філія відділення № 7854 публічного акціонерного товариства «Ощадбанк України» | Кредитуванняпідприємств малого та середньогобізнесу | Корисно |
|  | Комерційний банк «Приватбанк» | Кредитуванняпідприємств малого та середньогобізнесу | Корисно |

The first partner is responsible for action implementation and should submit an action progress report not later than 10.01.2020, 10.07.2020 and 10.01.2021 to the Plan Implementation Monitoring Committee.

At the exchange rate of the NBU as of 15.01.2019 (UAH 3,213.4747 per EUR 100).

At the exchange rate of the NBU as of 15.01.2019 (UAH 3,213.4747 per EUR 100)